## Timeline
Account: HRSS
Project: CAN
Tool Name: SOX Control Tool
Description: SOX Control Automation SAP-PPS Reconciliation
95%
STAGES | ESTIMATED WORKS IN HOURS | TARGET START DATE | TARGET END DATE | ACTUAL WORKING HOURS | ACTUAL START DATE | ACTUAL END DATE | % DONE | COMPLETED BY | REMARKS
Analyze | 9 |  |  | 10 |  |  | 100%
Tech Assessment | 2 | 2018-10-02 | 2018-10-02 | 3 | 2018-10-02 | 2018-10-02 | 100% | ronna.m.nahid
RTM Documentation | 4 | 2018-10-03 | 2018-10-04 | 4 | 2018-07-12 | 2018-07-17 | 100% | ronna.m.nahid
Data Gathering | 3 | 2018-10-08 | 2018-10-09 | 3 | 2018-07-18 | 2018-07-18 | 100% | ronna.m.nahid
Build | 80 |  |  | 40 |  |  | 100%
User Detection | 8 | 2018-12-10 | 2018-12-14 | 8 | 2018-12-10 | 2018-12-14 | 100% | jimmy.n.lacanaria.jr | transitioned
Establish database | 8 | 2018-12-17 | 2018-12-21 | 8 | 2018-12-17 | 2018-12-21 | 100% | jimmy.n.lacanaria.jr
CRUD functionality from Excel to Access | 40 | 2019-01-08 | 2019-01-12 | 8 | 2019-01-08 | 2019-01-12 | 100% | jimmy.n.lacanaria.jr
IP Lead additional functionality | 8 | 2019-01-15 | 2019-01-19 | 8 | 2019-01-15 | 2019-01-19 | 100% | jimmy.n.lacanaria.jr
Archive system | 16 | 2019-01-22 | 2018-01-25 | 8 | 2019-01-22 | 2018-01-25 | 100% | jimmy.n.lacanaria.jr
Test | 24 |  |  | 24 |  |  | 100%
Functional Test | 8 | 2018-08-17 | 2018-08-17 | 8 | 2018-08-17 | 2018-08-17 | 100% | jimmy.n.lacanaria.jr
Bug Fixing | 8 | 2018-08-20 | 2018-08-20 | 8 | 2018-08-20 | 2018-08-20 | 100% | jimmy.n.lacanaria.jr
Regression Test | 8 | 2018-08-21 | 2018-08-21 | 8 | 2018-08-21 | 2018-08-21 | 100% | jimmy.n.lacanaria.jr
Deploy | 40 |  |  | 8 |  |  | 80%
UAT | 40 | 2019-01-28 | 2018-08-29 | 8 | 2019-01-28 | 2018-08-29 | 80% | jimmy.n.lacanaria.jr
Vacation/SL Section
Date | VL/SL